## cover
Control Page
Solution | UAT SCRIPT FOR SORA UNION QA TEST |  |  | Test Module
Test Type | FUNCTIONAL |  |  | Test Cycle | 1st
Version
System(s) | Cura Healthcare portal & dummy.restapiexample api services
Test Objectives
The objective of this test is to validate the following: i. automate backend services ii. confirm user functionalities for CURA healthcare web portal works as expected
Test Requirements: To perform this test, the following would be required;
1. Test Cases
2. Test user data
3. API details
|  | Yes | No
Were all tests completed as expected? |  |  |  | Total Pass: | 11
Test Script completion logged? |  |  |  | Total Fail: | 2
|  |  |  | Total Partial | 0
|  |  |  | Total N/A: | 0
|  |  |  | Total Tests: | 13
DOCUMENT HISTORY
Tested by | Type of test performed | Date | Link to Requirement Document |  | Version Number
Agba-ogbonna Emmanuel | Functional | 21/12/2023 |  |  | 1

## ACCESSPAY-ENHANCEMENT- SPRINT 1 (hidden)
FUNCTIONAL TEST SCRIPT FOR ACCESSPAY ENHANCEMENT
| Test URL: | http://10.1.7.116:8699/Account/Login
| Application Developer | Gafar Babatunde
| Business Analyst /Users | Adeola Conde/Mobolaji Odumosu
| Testing Start Date | 10th June 2020
| Testing End Date | 15th June, 2020
| Quality Assurance & SoftwareTesting: | Fayokemi Akintunde
| Test Cycle | 1st Cycle
S/N | Test Scenario | Test Cases | Test Objective | Precondition | Test Steps | Expected Results | Actual Result | Test Result | Screenshot/Comment
AP-001 | Login | Login with valid credentials | This is to verify that a valid admin user can access the Admin portal successfully | The user must have been profiled on the application as an admin and must be logging in with valid AD Credentials | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. | The User should login successfully and the dashboard should be displayed | The user could login successfully and the dashboard was displayed. | PASS
AP-002 |  | Login with a Non-Admin User | This is to verify that a non- admin user cannot acccess the admin portal . | A non Admin user account | 1. Launch the admin portal url 2. Input the non-admin Username 3. Input password 4. Click on the login button. | An error message ' you are not authorized to use this portal 'should be displayed. | An error message ' you are not authorized to use this portal ' was displayed. | PASS
AP-003 |  | Login with invalid credentials | This is to verify that an unregistered user cannot access the admin portal | An unregistered AD User | 1. Launch the admin portal url 2. Input invalid Username or Password 3. Click on the login button. | An error message ' you are not authorized to use this portal 'should be displayed. | An error message ' you are not authorized to use this portal ' was displayed. | PASS
AP-004 | Biller Onboarding | Onboard Biller | This is to verify that a new biller can be created on AccessPay and channels enabled for the biller | The biller must have an account with AccessBank | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Onboard Biller tile 7. Populate the fields 8. Enable Channels | The Onboarding request should read pending and be available on the approver's queue | The Onboarding request read pending and was available on the approver's queue | PASS
AP-005 |  | Approve Biller Creation | This is to verify that A biller created can be approved for use | The biller must have been successfully created. The Approver must not be the same person that created the biller | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Approvals tile 7. Click the view button against the biller record to be approved 8. Select the Approve button | The biller should be successfully approved and be available on the biller dashboard | The biller should was successfully approved and is available on the billers dashboard | PASS
AP-006 |  | Update Biller Record | This is to verify that a biller's record can be successfully updated. | The biller record must already exist. Update must proceed for Approval before its effected. | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Approvals tile 7. click the edit button against biller whose record you want to update 8. update record accordingly 8. Submit for approval | Records should update accordingly and should be available for approval on the approver's queue. | The Billers record was successfully updated. | PASS
AP-007 |  | Approve Biller Record Update | This is to verify that an updated record undergoes approval before its effected. | The biller record must have been updated. The approver must be a different user from the person who made the updatre on the biller's record. | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Approvals tile 7. Click the view button against the biller record to be approved 8. Select the Approve button | Records should be successfully approved and be available for use at collections | The Billers record update was successfully approved. | PASS
AP-008 | Product Maintenance | Create Product: | This is to verify that products can be created maintaining the product description, Code and Credit Account | The biller you want to create products for must already exist and be approved. | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Products tile 7. populate the fields provided including (product description, product code, credit account 8. Submit the record created for approval | Products should be successfully created and then it is sent for approval. | The product was successfully created and it proceeded for approval | PASS
AP-009 |  | Enable Channel | This is to verify that an admin can enable the channels where the created product will be available for use. | A biller and her products must exist. Channels available at this point must also be channels enabled for biller during onboarding | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Products tile 7. populate the fields provided including (product description, product code, credit account. 8.Select channels where the products will be available on. 9. Submit the record created for approval | Channels enabled will apply and will proceed for approval. | The channels applied as selected and request went for approval | PASS
AP-010 |  | Setup Custom Fields | This is to verify that the following custom fields can be defined for a biller for specific collections: Text Number Email Date Dropdownlist | A biller must exist and there should be need to capture other data that the provided generic form doesn't suffice for. | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Products tile 7. populate the fields provided including (product description, product code, credit account. 8.Select channels where the products will be available on. 9. Select from the Custom fields dropdown the kind of custom field you wish to create (Text, Number, Email, Date or List). N:B: For dropdown list the values field should contain list values separated with comma without any space as in 31,32,33... 10. Input the field description and select channels you want it to apply to and submit for approval | The Custom fields will be successfully created and be available for use on the collections screen | The custom fields were successfully created . | PASS | The collection screen is still being developed so we are unable to see how it renders, however the expectation is for the created custom fields to be displayed per biller.
AP-011 |  | Approve Product Creation | This is to verify that products created proceed for approval before they are available for use at collections | Product must have been created successfully for the biller. Approver must be a different user from the creator | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Approval tile 7. Click on the product sub-tab 8. Click on the view button in front of the product to be approved. 9. Click on the aapprove button. | The Product will be successfully approved and be available for use on the collections interface. | The product created was successfully approve d for use. | PASS
AP-012 | Fees Management | Create Fees | This is to verify that a biller can create fees for different collection types that they desire. | The biller must have been successfully created and approved. The billers products (collection types) must have been created and also approved. | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Add Fees tiles 7. Select the biller and product 8. Populate the feees form 9. Click on the save button. | The fee should be created successfully | The fee was successfully added to the billers collection | PASS

## SPRINT 2- ACCESSPAY ENHANCE (2) (hidden)
UAT SCRIPT FOR ACCESSPAY ENHANCEMENT SPRINT 2
| Test URL: | http://10.1.7.116:8699/Account/Login https://10.1.7.116:2020/Narration
| Application Developer | Gafar Babatunde
| Business Analyst /Users | Adeola Conde/Mobolaji Odumosu
| Testing Start Date | 13th July 2020
| Testing End Date | 4th August 2020
| Quality Assurance & SoftwareTesting: | Fayokemi Akintunde
| Test Cycle | 1st Cycle
S/N | Test Scenario | Test Cases | Test Objective | Precondition | Test Steps | Expected Results | Actual Result | Test Result | Screenshot/Comment
AP-001 | Login | Login with valid credentials | This is to verify that a valid admin user can access the Admin portal successfully | The user must have been profiled on the application as an admin and must be logging in with valid AD Credentials | 1. Launch the admin portal url: http://10.1.7.116:8699/Account/Login 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. | The User should login successfully and the dashboard should be displayed | The user could login successfully and the dashboard was displayed. | PASS
AP-002 |  | Login with invalid credentials | This is to verify that an unregistered user cannot access the admin portal | An unregistered AD User | 1. Launch the admin portal url- http://10.1.7.116:8699/Account/Login 2. Input invalid Username or Password 3. Click on the login button. | An error message ' you are not authorized to use this portal 'should be displayed. | An error message ' you are not authorized to use this portal ' was displayed. | PASS
AP-003 | Biller Onboarding | Make the Biller Name field editable | This is to verify that when creating a new biller the biller name field is editable | An inputter must have initiated Biller Onboarding | 1. Launch the admin portal url - http://10.1.7.116:8699/Account/Login 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Input the Biller Name on the Biller name field 7. Input other details required and submit | The Biller Name field should be editable and data inputted should be sent to the Approver for approval | The Biller Name field was editable and data inputted was sent to the Approver for approval | PASS
AP-004 |  | Make the description field accept a brief description of what the biller's business entails | This is to verify that a brief description of the biller's business can be inputted on the description field | An inputter must have initiated Biller Onboarding | 1. Launch the admin portal url - http://10.1.7.116:8699/Account/Login 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Input the Biller's business description on the description field. 7. Input other details required and submit | The description field should allow for brief description of biller's business to be inputted and data inputted should be sent to the Approver for approval | The description field allowed for brief description of biller's business to be inputted and data inputted was sent to the Approver for approval | PASS
AP-005 |  | Category Maintenance | This is to verify that category types can be maintained on the application | User must be a Valid NT user | 1. Launch the admin portal url - http://10.1.7.116:8699/Account/Login 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Category Maintenance Tile 7. Create New Category 8. Submit | Category should be successfully created | Category was created successfully created. | PASS
AP-006 |  | Auto generation of Biller Code | This is to verify that when new billers are created the biller codes are automatically generated | A new biller must have been created. The Biller Code field must not be editable | 1. Launch the admin portal url - http://10.1.7.116:8699/Account/Login 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Onboard Biller tile 7. Input all biller details required for biller creation 8. Submit | The Biller Code should be autogenerated and should reflect on the record sent to the Authorizer for Approval. | The Biller Code is autogenerated and reflects on the record sent to the Authorizer for Approval. | PASS
AP-007 | Product Maintenance | Auto generation of Product Code | This is to verify that when products are created under specific billers, the product codes are automatically generated | A new product must have been created. The Product Code field must not be editable. | 1. Launch the admin portal url - http://10.1.7.116:8699/Account/Login 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Products tile 7. populate the fields provided 8. Submit the record created for approval | Products code should be auto generated and record should be sent to authorizer for approval | The product code was automatically generated and it proceeded for approval | PASS
AP-008 | Simple Biller Onboarding (USSD) | Simple Biller Onboarding On USSD (Single Account) | This is to verify that Simple Billers with single acces bank accounts can initiate an onboarding request via USSD | The biller must be a valid Access Bank Account holder User must have only one valid Access bank Account | 1. User dials the USSD String (*901*997*1#). 2. Input Business Name 3. Inputs Yes/No to the Phone Number Reference Question 4. Submit N:B: (*901*997*1#). | System should display a message for successful submission of request | The system displayed message ' Your Request has been Logged Successfully' | PASS
AP-009 |  | Simple Biller Onboarding On USSD (Multiple Accounts) | This is to verify that Simple Billers with multiple acces bank accounts can initiate an onboarding request via USSD | The biller must be a valid Access Bank Account holder User must have more than one valid Access bank Account | 1. User dials the USSD String (*901*997*1#). 2. Input Business Name 3. Inputs Yes/No to the Phone Number Reference Question 4. Selects Credit Account from the options provided 5. Submit N:B: USSD String: (*901*997*1#). Mobile Network Used: 9mobile | System should display a message for successful submission of request | The system displayed message ' Your Request has been Logged Successfully' | PASS
AP-010 | Fees Management | Create Fees & Map Channels to Fees | This is to verify that Fees can be successfully created and channels mapped to fees created. | Products must have been created for th biller | 1. Launch the admin portal url 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Maintenance Menu 6. Click on the Add Fees tiles 7. Select the biller and product 8. Populate the fees form 9. Check the Channels you want the fees to be applicable on 9. Click on the save button. | The fee should be created successfully with the enabled channel mapped accordingly. | The fee was successfully added to the billers collection displaying the channels enabled for it. | PASS
AP-011 | Narration Maintenance (Create Narration) | Slash Narration Format | This is to verify that the slash Narration format can be defined for a specific biller | Biller must exists with product or collections. Generic and Unique fields must have been created for Biller's collections. | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Add Narration Format 7. Select the biller and product from the drop downlist 8. Select slash option from the separators dropdown list 9. Add the fields you want to reflect on the Narration 9. Define the character length of each field selected 10. Click on the Add Narration button to save after adding all required fields. | The Slash separated Narration Format should be successfully created and proceed for approval | The slash separated Narration format was successfully created and was sent for Approval | PASS
AP-012 |  | Semi Colon Narration Format | This is to verify that the Semi-colon Narration format can be defined for a specific biller | Biller must exists with product or collections. Generic and Unique fields must have been created for Biller's collections. | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Add Narration Format 7. Select the biller and product from the drop downlist 8. Select Semi-colon option from the separators dropdown list 9. Add the fields you want to reflect on the Narration 9. Define the character length of each field selected 10. Click on the Add Narration button to save after adding all required fields. | The Semi-colon Seperated Narration Format should be successfully created and proceed for approval | The Semi-Colon Separated Narration format was successfully created and was sent for Approval | PASS
AP-013 |  | Space Narration Format | This is to verify that the Space Narration format can be defined for a specific biller | Biller must exists with product or collections. Generic and Unique fields must have been created for Biller's collections. | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Add Narration Format 7. Select the biller and product from the drop downlist 8. Select Comma option from the separators dropdown list 9. Add the fields you want to reflect on the Narration 9. Define the character length of each field selected 10. Click on the Add Narration button to save after adding all required fields. | The Comma Seperated Narration Format should be successfully created and proceed for approval | The Comma Separated Narration format was successfully created and was sent for Approval | PASS
AP-014 |  | Comma Narration Format | This is to verify that the Comma Narration format can be defined for a specific biller | Biller must exists with product or collections. Generic and Unique fields must have been created for Biller's collections. | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Add Narration Format 7. Select the biller and product from the drop downlist 8. Select Space option from the separators dropdown list 9. Add the fields you want to reflect on the Narration 9. Define the character length of each field selected 10. Click on the Add Narration button to save after adding all required fields. | The space Seperated Narration Format should be successfully created and proceed for approval | The space Separated Narration format was successfully created and was sent for Approval | PASS
AP-015 |  | Character Length of Narration Fields | This is to verify that the character length of Narration fields can be defined on the application. | Biller must exists with product or collections. Generic and Unique fields must have been created for Biller's collections. | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Add Narration Format 7. Select the biller and product from the drop downlist 8. Select desired option from the separators dropdown list 9. Add the fields you want to reflect on the Narration | The character length popup should be displayed | The character length popup was displayed as expected. | PASS
AP-016 | Approve Biller's Narration Format | Approve Narration Format | This is to verify that a defined Narration Format can be approved. | Narration formats must have been created for the Biller. User to approve must have approving rights | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Pending Narration Formats sub menu 7. Select the record to be approved 8. Review and approve. N:B: New Approvals override existing records of Narration formats | The Created Narration format should be successfully approved if satisfactory | The Created Narration Format was successfully approved. | PASS
AP-017 | Decline Narration Format Approval Request | Decline Narration Format Approval Request | This is to verify that an unsatisfactory Narration format can be declined by the approver | Narration formats must have been created for the Biller. User to approve must have approving rights | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Pending Narration Formats sub menu 7. Select the record to be approved 8. Click the delete button and confirm decline. | The record should be successfully deleted from the system and should not apply to the biller | The record was deleted successfully and didn't apply to the biller | PASS
AP-018 | View Biller's Narration Format | View Narration Formats | This is to verify that Narration formats created can be viewed on a grid. | Narration formats must have been created for the Biller | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Narration Maintenance Menu 6. Click on the Narration Formats sub menu 7. View records | The Narration Formats defined should be displayed on this list | The Narration Formats defined were displayed on the list | PASS
AP-019 | Report Format Maintenance | Create Biller Report Format | This is to verify that a biller's report format can be created on the application | Biller must exists with product or collections. Generic and Unique fields must have been created for Biller's collections. | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Report Format Maintenance Menu 6. Click on the Add Narration Format 7. Select the biller and product from the drop downlist 8. Select Space option from the separators dropdown list 9. Add the fields you want to reflect on the Narration 9. Define the character length of each field selected 10. Click on the Add Narration button to save after adding all required fields. | The report format should be successfully created and proceed for approval | The report format was successfully created and was sent for approval | PASS
AP-020 |  | Approve Report Format | This is to verify that the created Report format can be successfully approved. | Report Formats must have been created | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Report Format Maintenance Menu 6. Click on the Pending Report Formats sub menu 7. Select the record to be approved 8. Review and approve. N:B: New Approvals override existing records of Report formats for the biller's collection | The record should be approved successfully | The record was successfully approved | PASS
AP-021 |  | Decline Report Format Approval Request | This is to verify that a Report format approval request can be declined if not satisfactory | Report Formats must have been created for the Biller | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Report Format Maintenance Menu 6. Click on the Pending Report Formats sub menu 7. Select the record to be approved 8. Click delete and confirm decline. | The record should be deleted from the application and shouldn't apply | The record was succesfully deleted and didn't apply to the biller's collections | PASS
AP-022 |  | View Report | This is to verify that a defined report can be viewed on the application. | A report type must have been created for the Biller | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Report Menu 6. Select Biller and collections 7. specify date range 8. View report | The Report should be displayed based on criteria specified | The Report was displayed as expected | PASS
AP-023 |  | Download Report | This is to verify that a defined report can be downloaded from the application. | Report must have been fetched | 1. Launch the admin portal url: https://10.1.7.116:2020/Narration 2. Input the valid admin ADUsername 3. Input valid admin password 4. Click on the login button. 5. Click on the Biller Report Menu 6. Select Biller and collections 7. specify date range 8. Download report | The Report spooled should download | The Report spooled downloaded as expected | PASS

## test cases
UAT SCRIPT FOR SORA UNION QA TEST
Project Name: | SORA UNION QA TEST
Business Analyst / Users | N/A
Start Date | 21/12/2023
End Date | 21/12/2023
Quality Assurance | Emmanuel Ikenna Agba-ogbonna
Cycle | 1
S/N | Test Scenerio | Test Cases | Test Objective | Test Data | Expected Results | Actual Result | Test Result | Test Class | screenshots | Comments
TST_CSE_01 | User Authentication | user login using invalid username | To confirm cannot login successfully using invalid username. | username: dummy text password: dummy text | user is not expected to login successfully. | As expected, user was unable to login succesfully. | PASS | Negative
TST_CSE_02 |  | user login using invalid password | To confirm cannot login successfully using invalid password. |  | user is not expected to login successfully. | As expected, user was unable to login succesfully. | PASS | Negative
TST_CSE_03 |  | User login using valid user details | To confirm user can login successfully using valid user details. | valid user data | user is expected to login successfully. | As expected, user was able to login succesfully. | PASS | POSITIVE
TST_CSE_04 |  | User logout | To confirm user can logout successfully | N/A | user is expected to logout successfully. | As expected, user was able to logout succesfully. | PASS | POSITIVE
TST_CSE_05 |  | Unauthorized user access | To confirm unauthorized user cannot access the website | N/A | unauthorized user is not expected to access the website successfully. | As expected, unauthorized user was unable to access the website. | PASS | POSITIVE
TST_CSE_06 | Book appointment | Book valid appointment | To confirm that users can successfully book appointment on the web application | Appointment data | user is expected to successfully book an appointment on the website | users was able to successfully book an application on the application | Passed | POSITIVE
TST_CSE_07 |  | Book appointment using invalid date | To confirm users cannot successfully book appointment on the web application using invalid date |  | user is not expected to successfully book an appointment on the website using invalid date | users was unable to successfully book an application on the application | PASS | POSITIVE
TST_CSE_08 |  | View appointment summary | To confirm user can view summary immediatly after booking appointment |  | user is expected to see appointment summary after booking appointment | user was able to see appointment summary after booking appointment | PASS | POSITIVE
TST_CSE_09 | Application History | View history page and confirm appointment exists | To confirm user can view application history page and confirm appointments are been displayed on the page. | N/A | User is expected to view the history page on his/her browser and also confirm records exist. | As expected, User was able to view the history page on his/her browser and also confirm records exist. | PASS | POSITIVE
TST_CSE_10 | Profile Page | View user profile page and confirm user data | To confirm user can access his/her profile page |  | User is expected to view profile page on his/her browser | user was unable to view profile page | FAILED | POSITIVE
TST_CSE_11 | API services Test | Fetch all employees | Confirm API service returns all emloyees record | test url | User is expected to confirm API service returned all emloyees record | As expected, user was able to confirm API service returned all emloyees record | PASS | POSITIVE
TST_CSE_12 |  | Fetch employee with ID 5 | Confirm API service returns record for employee with ID 5 | test url ID | User is expected to confirm API service returned record for emloyee with ID 5 | User was unable to confirm API service returned record for emloyee with ID 5 | FAILED | POSITIVE
TST_CSE_13 |  | Fetch employee with invalid ID | Confirm API service does not returned record using invalid id |  | User is expected to confirm API service does not return record using invalid ID | User was able to confirm no record was returned | PASS | NEGATIVE

## summary
Good day All,
Kindly find below test report for the SORA UNION QA TEST
Project Name: | SORA UNION QA TEST
Business User: | N/A
Test Start Date: | 21/12/2023
Test End Date: | 21/12/2023
Name Of Tester: | Agba-ogbonna Emmanuel Ikenna
The result of the SORA UNION QA TEST are as follows: 13 – planned test,
13 – executed, 00– test case not tested, 11– passed, 02 – failed.
DEFECTS | Number
Total number of defects | 2
Functional defects | 1
Usability | 1